## Slide 1: Software Requirements Engineering
Lectures 28 & 29
Requirements Management

## Slide 2: Requirements Management
Software change isn’t a bad thing; in fact, it’s necessary.
It’s virtually impossible to define all of a product’s requirements up front.
The world changes as development progresses:
  New market opportunities arise,
  Regulations and policies change,
  Business needs evolve.
An effective software team can nimbly respond to necessary changes so that the product they build provides timely customer value.
Having great requirements gets you only partway to a solution; they also have to be well managed and effectively communicated among the project participants.

## Slide 3: Sub-disciplines of software requirements engineering.

## Slide 4: Boundary between Requirements Development and Requirements Management

## Slide 5: Requirements baseline
Requirements development involves activities to
  elicit,
  analyze,
  specify,
  and validate a software project’s requirements.
Requirements development deliverables include business requirements, user requirements, functional and nonfunctional requirements, a data dictionary, and various analysis models.
After they are reviewed and approved, any defined subset of these items constitutes a requirements baseline.
A requirements baseline is a set of requirements that stakeholders have agreed to, often defining the contents of a specific planned release or development iteration.
At the time a set of requirements is baselined—typically following review and approval—the requirements are placed under configuration (or change) management.
Subsequent changes can be made only through the project’s defined change control procedure.

## Slide 6: Activities in Requirements Management

## Slide 7: Costs of accepting changes
A development team that accepts proposed requirement changes or additions might not be able to fulfill its existing schedule and quality commitments.
The project manager must negotiate changes to those commitments with affected managers, customers, and other stakeholders. The project can accommodate new or changed requirements in various ways:
  By deferring lower-priority requirements to later iterations or cutting them completely
  By obtaining additional staff or outsourcing some of the work
  By extending the delivery schedule or adding iterations to an agile project
  By sacrificing quality to ship by the original date

## Slide 8: 1. Requirements version control
Version control—uniquely identifying different versions of an item—applies at the level of both individual requirements and requirements sets, most commonly represented in the form of documents.
Begin version control as soon as you draft a requirement or a document so you can retain a history of changes made.
Every version of the requirements must be uniquely identified.
Every team member must be able to access the current version of the requirements.
Changes must be clearly documented and communicated to everyone affected.
To minimize confusion and miscommunication, permit only designated individuals to update the requirements, and make sure that the version identifier changes whenever an update is made.
Each circulated version of a requirements document or each requirement in a tool should include a revision history that identifies
  the changes made,
  the date of each change,
  the individual who made the change,
  and the reason for each change.

## Slide 9: Use of RM tool or Word Processor for Version Control
The most robust approach to version control is to store the requirements in a requirements management tool.
RM tools track the history of changes made to every requirement, which is valuable when you need to revert to an earlier version.
Such a tool allows for comments describing the rationale behind a decision to add, modify, or delete a requirement. These comments are helpful if the requirement becomes a topic for discussion again in the future.
If you’re storing requirements in documents, you can track changes by using the word processor’s revision marks feature.
When you baseline a document, first archive a marked-up version, then accept all the revisions, and then store the now clean version as the new baseline, ready for the next round of changes.

## Slide 10: Manual Version Control
The simplest version control mechanism is to manually label each revision of a document according to a standard convention.
You can label the first version of any new document with its title and “Version 1.0 draft 1.”
The next draft keeps the same title but is identified as “Version 1.0 draft 2.”
The author increments the draft number with each iteration until the document is approved and baselined.
At that time, the version identifier is changed to “Version 1.0 approved,” again keeping the same document title.
The next version is either “Version 1.1 draft 1” for a minor revision or “Version 2.0 draft 1” for a major change.
This scheme clearly distinguishes between draft and baselined document versions, but it does require manual discipline on the part of those who modify the documents.

## Slide 11: Requirements Attributes
In addition to its textual description, each requirement should have supporting pieces of information or attributes associated with it.
These attributes establish a context and background for each requirement.
RM tools typically provide several system-generated attributes in addition to letting you define others, some of which can be automatically populated.
The tools let you query the database to view selected subsets of requirements based on their attribute values
Following is a list of potential requirement attributes to consider:
  Date the requirement was created
  Current version number of the requirement
  Author who wrote the requirement
  Priority
  Status
  Origin or source of the requirement
  Rationale behind the requirement
  Release number or iteration to which the requirement is allocated
  Stakeholder to contact with questions or to make decisions about proposed changes
  Validation method to be used or acceptance criteria

## Slide 12: 2. Tracking requirements status
Software developers are sometimes overly optimistic when they report how much of a task is complete.
Tracking the status of each functional requirement throughout development provides a more precise gauge of project progress.
Tracking status means comparing where you really are at a particular time against the expectation of what “complete” means for this development cycle.
You might have planned to implement only certain flows of a use case in the current release, leaving full implementation for a future release.
Monitor the status of just those functional requirements that were committed for the current release, because that’s the set that’s supposed to be 100 percent done before you declare success and ship the release.

## Slide 13: 3. Change Control
Most developers have encountered an apparently simple change that turned out to be far more complicated than expected.
Additionally, when developers who want to be accommodating agree to add enhancements that users request, requirements changes slip in through the back door instead of being approved by the right stakeholders.
Such uncontrolled change is a common source of project chaos, schedule slips, quality problems, and hard feelings.

## Slide 14: 3. Change Control
An organization that’s serious about managing its software projects must ensure that:
  Proposed requirements changes are thoughtfully evaluated before being committed to.
  Appropriate individuals make informed business decisions about requested changes.
  Change activity is made visible to affected stakeholders.
  Approved changes are communicated to all affected participants.
  The project incorporates requirements changes in a consistent and effective fashion.

## Slide 15: Managing scope creep
Requirements growth includes new functionality and significant modifications that are presented after a set of requirements has been .
The longer a project goes on, the more growth it experiences.
Some requirements evolution is legitimate, unavoidable, and even advantageous.
Scope creep, though, in which the project continuously incorporates more functionality without adjusting resources, schedules, or quality goals, is insidious.
If every proposed change is approved, it might appear to stakeholders that the software will never be delivered—and indeed, it might not.

## Slide 16: Steps to manage Scope Creep
The first step in managing scope creep is to document the business objectives, product vision, project scope, and limitations of the new system.
Evaluate every proposed requirement or feature against the business requirements.
Engaging customers in elicitation reduces the number of requirements that are overlooked.
Prototyping helps to control scope creep by helping developers and users share a clear understanding of user needs and prospective solutions.
Using short development cycles to release a system incrementally provides frequent opportunities for adjustments.
The most effective technique for controlling scope creep is the ability to say “no“.
People don’t like to say “no,“ and development teams can receive intense pressure to always say “yes.“

## Slide 17: Change control policy
Management should communicate a policy that states its expectations of how project teams will handle proposed changes in requirements and all other significant project artifacts.
The following change control policy statements can be helpful:
  All changes must follow the process. If a change request is not submitted in accordance with this process, it will not be considered.
  No design or implementation work other than feasibility exploration will be performed on unapproved changes.
  Simply requesting a change does not guarantee that it will be made. The project’s change control board (CCB) will decide which changes to implement.
  The contents of the change database must be visible to all project stakeholders.
  Impact analysis must be performed for every change.
  Every incorporated change must be traceable to an approved change request.
  The rationale behind every approval or rejection of a change request must be recorded.

## Slide 19: Change Control Board
The change control board is the body of people—whether it is one individual or a diverse group—that decides which proposed changes and new requirements to accept, which to accept with revisions, and which to reject.
CCB composition
The CCB membership should represent all groups who need to participate in making decisions within the scope of that CCB’s authority. Consider selecting representatives from the following areas:
  Project or program management
  Business analysis or product management
  Development
  Testing or quality assurance
  Marketing, the business for which the application is being built, or customer representatives
  Technical support or help desk
Only the subset of these people who need to make the decisions will be part of the CCB, although all stakeholders must be informed of decisions that affect their work.

## Slide 20: Change impact analysis
The need for impact analysis is obvious for major enhancements.
However, unexpected complications can lurk below the surface of even minor change requests.
Impact analysis is a key aspect of responsible requirements management.
It provides an accurate understanding of the implications of a proposed change, which helps the team make informed business decisions about which proposals to approve.
The analysis examines the request to identify components that might have to be created, modified, or discarded, and to estimate the effort required to implement the change.
Before a developer says, “Sure, no problem” in response to a change request, he should spend a little time on impact analysis.

## Slide 21: Impact analysis procedure
The CCB Chair will ask one or more technical people (business analysts, developers, and/or testers) to perform the impact analysis for a specific change proposal.
Impact analysis involves three steps:
  Understand the possible implications of making the change.
    A requirement change often produces a large ripple effect, leading to modifications in other requirements, architectures,designs, code, and tests.
    Changes can lead to conflicts with other requirements or can compromise quality attributes, such as performance or security.
  2. Identify all the requirements, files, models, and documents that might have to be modified if the team incorporates the requested change.
  3. Identify the tasks required to implement the change, and estimate the effort needed to complete those tasks.

## Slide 22: 4. Tracing Requirements
Requirements trace information documents the dependencies and logical links between individual requirements and other system elements.
These elements include other requirements of various types, business rules, architecture and other design components, source code modules, tests, and help files.
Trace information facilitates impact analysis by helping you identify all the work products you might have to modify to implement a proposed requirement change.

## Slide 23: Tracing Requirements
Trace links allow you to follow the life of a requirement both forward and backward, from origin through implementation.
Traceability is one of the characteristics of excellent requirements.
For requirements to be traceable, each one must be uniquely and persistently labeled so that you can refer to it unambiguously throughout the project.

## Slide 24
Four types of requirements tracing

## Slide 25: Forward and Backward Traceability
Customer needs (business objectives, market demands, and/or user requirements) are traced forward to requirements, so you can tell which requirements will be affected if those needs change during or after development.
A complete set of forward traces also gives you confidence that the requirements set has addressed all stated customer needs.
Conversely, you can trace backward from requirements to customer needs to identify the origin of each software requirement.

## Slide 26: Forward and Backward Traceability
The bottom half of the figure indicates that, as requirements flow into downstream deliverables during development, you can trace forward from requirements by defining links between individual functional and nonfunctional requirements and specific system elements.
This type of link allows you to determine that you’ve satisfied every requirement because you know which design components and code elements address each one.
The fourth type of link traces specific product elements backward to requirements so that you know why each element was created.
Most applications include some scaffolding or enabling code, such as for testing, that doesn’t relate directly to user-specified requirements, but you should know why each line of code was written.

## Slide 27: Forward and Backward Traceability
Suppose a tester encounters unexpected functionality with no corresponding written requirement. This code could indicate that
  a developer implemented a legitimate implied or verbally communicated requirement that the business analyst can now add to the requirements set.
  Alternatively, it might be “orphan code,” an instance of gold-plating that doesn’t belong in the product.
Conversely, tests that are derived from—and traced back to—individual requirements provide a mechanism for detecting unimplemented requirements, because the expected functionality will be missing from the system being tested.
Trace links also help you keep track of parentage, interconnections, and dependencies among individual requirements.

## Slide 28
Some possible requirements trace links.

## Slide 29: Motivations for tracing requirements
Finding missing requirements
Finding unnecessary requirements
Certification and compliance
Change impact analysis
Maintenance
Project tracking
Reengineering
Reuse
Testing

## Slide 30: Traceability Matrix
The most common way to represent the links between requirements and other system elements is in a requirements traceability matrix, also called a requirements trace matrix or a traceability table.
Consider the table below which illustrates a portion of a requirements traceability matrix, drawn from the Chemical Tracking System

## Slide 31: The requirements traceability matrix
Another way to represent trace information is through a set of matrices that define links between pairs of system elements, such as these:
One type of requirement to other requirements of that same type
One type of requirement to requirements of another type
One type of requirement to tests

## Slide 32: Different types of trace links
One-to-one
  One design element is implemented in one code module.
One-to-many
  One functional requirement is verified by multiple tests.
Many-to-many
  Each use case leads to multiple functional requirements, and certain functional requirements are common to several use cases.

## Slide 33
Requirements traceability matrix showing links between use cases and functional requirements

## Slide 34: Traceability of non-functional requirements
Cerain quality attributes often do not trace directly into code.
  A response-time requirement might dictate the use of certain hardware, algorithms, database structures, and architectural approaches.
  A portability requirement could restrict the language features that the programmer uses but might not result in specific code segments that enable portability.
Other quality attributes are indeed implemented in code.
Security requirements for user authentication lead to derived functional requirements that might be implemented through passwords or biometrics functionality.

## Slide 35
Sample traceability chain for requirements dealing with application security.